## Members List
Group 6 | TickIt (Theater Ticket Manager)
Name | Primary Role | Email | Cell phone | Class01 | Class02 | Class03 | Class04 | Class05 | Work Schedule | Other Conflicts
Patrick Berzins | GUI Lead | prb0013@uah.edu | 3176704605 | M/W 11-12:50 | M 5:50-8:40 | T/H 1-2:30 |  |  | T/H 7-1 F 7-2:30
Jayde Holbrook | Team Lead | cjh0051@uah.edu | 6063167433 | M/W 11:20-12:40 | M/W 1:00-2:20 | T/TH 9:40-11:00 | M/W 6:00-7:20 | M 9:40-10:35 | T: 11:30-1:00 PM, T/TH: 6:30-9:00 PM, SU 4:30-9:00 PM
Van Hudson | Technical Writer | van.hudson@uah.edu | 7703286018 | M/W 11:30-2:00 | T/TH 11:30-2:00 | W 5:50-8:40 |  |  | M, T, Th 8am-11am; W 3pm-5pm; F 8am-5pm | M 7pm-12am
Ben Lukins | Test Lead | bal0015@uah.edu | 2563615952 | M/W 9:40-11 | T/Th 1-2:20 |  |  |  | Variable, usually M/W/F 11-5
Nathaniel Smith | Technical Lead | cns0030@uah.edu | 2703175084 | M/W 11-1 | [5 empty] | F 6-9
https://lettucemeet.com/l/6POZp

## Key Decisions
Key Decision ID | Date | Decision
KD-01 | 2023-01-19 | We will be using GitHub to work collaboratively
KD-02 | 2023-01-19 | We will be using Jira for bug tracking and agile project management
KD-03 | 2023-01-24 | We will be using Firebase as our database and web hosting solution
KD-04 | 2023-01-24 | We will be using React JS as our frontend framework
KD-05 | 2023-01-31 | All shows will be shown together and not separated by venue
KD-06 | 2023-01-31 | Rather than adding tickets to a "cart" for purchase, users will be taken directly to a payment page after selecting their seat
KD-07 | 2023-01-31 | Shows will automatically be filtered by date when viewing all of the shows
KD-08 | 2023-01-31 | All ticket purchases will come with a unique confirmation code as proof of purchase
KD-09 | 2023-02-07 | We will use Figma to develop a GUI prototype
KD-10 | 2023-02-12 | We will use Lucidchart to create our UML Diagram
KD-11 | 2023-02-28 | We will be using Node.JS and React.JS to build our web app
KD-12 | 2023-03-02 | We will be using Typescript
KD-13 | 2023-03-30 | Frontend will be using JavaScript
KD-14 | 2023-04-17 | Concert Hall is always 0 in System.venue

## Meetings
|  |  |  | Team Members in Attendance |  |  |  |  | Meeting Notes
Meeting ID | Date | Time | Duration (hrs) | Patrick Berzins | Jayde Holbrook | Van Hudson | Ben Lukins | Nathaniel Smith | Click here for all meeting notes
M-01 | 2023-01-17 | 16:20 | 1.0 hrs | Present | Moderator | Recorder | Present | Present
M-02 | 2023-01-19 | 15:00 | 1.0 hrs | Present | Moderator | Present | Present | Present
M-03 | 2023-01-19 | 17:00 | 0.6 hrs | Present | Present | Present | Present | Present
M-04 | 2023-01-24 | 15:00 | 1.1 hrs | Present | Present | Recorder | Present | Present
M-05 | 2023-01-24 | 17:00 | 0.6 hrs | Present | Present | Present | Present | Present
M-06 | 2023-01-26 | 3:00:00 PM | 0.9 hrs | Present | Moderator | Recorder | Present | Present
M-07 | 2013-01-31 | 15:00 | 1.0 hrs | Present | Moderator | Recorder | Present | Present
M-08 | 2023-02-02 | 15:00 | 1.1 hrs | Present | Moderator | Recorder | Present | Present
M-09 | 2023-02-02 | 17:06 | 0.3 hrs | Present | Present | Present | Present | Present
M-10 | 2023-02-07 | 15:00 | 1.0 hrs | Present | Moderator | Present | Present | Present
M-11 | 2023-02-09 | 15:00 | 1.0 hrs | Present | Moderator | Present | Present | Present
M-12 | 2023-02-09 | 16:25 | 1.0 hrs | Present | Present | Present | Present | Present
M-13 | 2023-02-14 | 15:00 | 1.1 hrs | Present | Moderator | Present | Present | Present
M-14 | 2023-02-21 | 15:00 | 0.5 hrs | Present | Absent - Known | Recorder | Present | Present
M-15 | 2023-02-23 | 15:00 | 1.1 hrs | Absent - Known | Moderator | Present | Present | Present
M-16 | 2023-02-28 | 15:00 | 1.2 hrs | Present | Moderator | Present | Present | Present
M-17 | 2023-03-02 | 15:00 | 1.6 hrs | Present | Moderator | Present | Present | Present
M-18 | 2023-03-04 | 13:00 | 1.4 hrs |  | Moderator |  | Present | Present | Backend Team Meeting
M-19 | 2023-03-07 | 15:00 | 0.9 hrs | Present | Moderator | Absent - Known | Present | Present
M-20 | 2023-03-09 | 15:00 | 1.9 hrs | Present | Moderator | Present | Present | Present
M-21 | 2023-03-21 | 15:00 | 0.5 hrs | Present | Moderator | Absent - Known | Present | Present
M-22 | 2023-03-28 | 15:00 | 1.2 hrs | Present | Moderator | Recorder | Present | Present
M-23 | 2023-03-30 | 15:00 | 2.5 hrs | Present | Moderator | Present | Present | Present
M-24 | 2023-04-04 | 15:00 | 1.2 hrs | Absent - Unknown | Moderator | Present | Present | Present
M-25 | 2023-04-06 | 15:00 | 1.2 hrs | Present | Absent - Known | Present | Present | Present
M-26 | 2023-04-11 | 15:00 | 1.2 hrs | Present | Moderator | Present | Present | Present
M-27 | 2023-04-11 | 17:24 | 0.4 hrs | Present | Present | Present | Present | Present
M-28 | 2023-04-13 | 15:00 | 1.2 hrs | Present | Moderator | Present | Present | Absent - Known
M-29 | 2023-04-15 | 11:00 | 2.2 hrs | Present | Moderator | Present | Present | Present
M-30 | 2023-04-15 | 14:10 | 4.0 hrs | Present | Moderator | Present | Present | Absent - Known
M-31 | 2023-04-16 | 12:00 | 4.2 hrs | Absent - Known | Moderator | Present | Present | Present
M-32 | 2023-04-17 | 15:00 | 8.1 hrs | Present | Moderator | Present | Present | Present
M-33 | 2023-04-18 | 14:00 | 2.2 hrs | Present | Moderator | Present | Present | Present
M-34 | 2023-04-20 | 15:00 | 1.1 hrs | Present | Moderator | Present | Present | Present
M-35 | 2023-04-23 | 12:00 | 7.0 hrs | Present | Moderator | Present | Present | Present
M-36 | 2023-04-27 | 16:00 | 4.0 hrs | Present | Moderator | Present | Present | Present

## Epics
Epic ID | Short Title | Description
Epic01 | Document Prep | As a developer, I want to prepare documents and presentations so that we can share our progress with the instructor and the class.
Epic02 | Testing | As a developer, I want to create a test plan and perform all test cases so that the application works as expected.
Epic03 | Ticket buyers | As a ticket buyer, I want to select and purchase a ticket so that I can see a performance at the Civic Center Playhouse or the Civic Center Concert Hall.
Epic04 | Ticket sellers | As an organization volunteer, I want to manage the tickets and their sales so that no seat is accidentally sold to more than one person.

## User Stories
Parent Epic ID | User Story ID | Title | Description | Assigned to - Primary | Assigned to - Secondary | Sprint Number
Epic01 | US-01 | Team Development Research | As a developer, I want to determine the best approach for development so that my team can begin developing the application. | ALL | ALL | 1
Epic01 | US-02 | SDP Document and Presentation | As a developer, I want to plan ahead and start making design/development decisions. | ALL | ALL | 1
Epic01 | US-03 | Creating User Stories/Requirements | As a developer, I want to create a list of features/requirements to keep in mind so that I can keep on schedule. | ALL | ALL | 2
Epic01 | US-04 | Clear GUI (Prototyping) | As a developer, I want to design and prototype a clear GUI so that users can use the application effectively. | ALL | ALL | 2
Epic02 | US-05 | Testing | As a developer, I want to thoroughly test the application to ensure that all major bugs and most minor bugs are taken care of. | Ben Lukins | Jayde Holbrook | 5
Epic03 | US-06 | User Guide | As a ticket buyer, I want to view a user guide that explains the process of buying tickets so that I may become familiar with the system | Jayde Holbrook | Van Hudson | 5
Epic03 | US-07 | User Filter by Venue | As a ticket buyer, I want to be able to filter performances by their venue so that I can see all the performances running in a particular location. | WITHDRAWN | WITHDRAWN | 4
Epic03 | US-08 | User Filter By Date | As a ticket buyer, I want to be able to filter performances by their date so that I can see all the performances running on a particular day. | WITHDRAWN | WITHDRAWN | 4
Epic03 | US-09 | User Filter by Category | As a ticket buyer, I want to be able to filter performances by their category so that I can see all performances that fall into a certain category. | WITHDRAWN | WITHDRAWN | 4
Epic03 | US-10 | User View Available Performances | As a ticket buyer, I want to view the available performances so that I can decide what performances I want to attend. | Ben Lukins | Van Hudson | 3
Epic03 | US-11 | User View Available Seats | As a ticket buyer, I want to view the available seats at my chosen performance and venue so that I can decide where I want to sit. | Van Hudson | Jayde Holbrook | 3
Epic03 | US-12 | User Performance Selection | As a ticket buyer, I want to select a certain performance so that I can see the available seats. | Ben Lukins | Van Hudson | 3
Epic03 | US-13 | User Seat Selection | As a ticket buyer, I want to select a certain seat so that I may purchase them at check-out. | Van Hudson | Ben Lukins | 3
Epic03 | US-14 | User Input Payment Information | As a ticket buyer, I want to input my payment information so that I may purchase my selected tickets. | Van Hudson | Jayde Holbrook | 4
Epic03 | US-15 | User Payment Method | As a ticket buyer, I want to be able to select my prefered payment method type so that I can pay for the tickets. | Van Hudson | Ben Lukins | 3
Epic03 | US-16 | Visual Seat Indiciation | As a ticket buyer, I want to visually see section indicators, row numbers, seat numbers, and indicators for wheelchair-accessible seating so that I can purchase the ticket that works best for me. | Van Hudson | Ben Lukins | 4
Epic03 | US-17 | Visual Indicator of Sold Seats (Public) | As a ticket buyer, I want to be able to see which seats are already taken so that I do not purchase a seat that is not available. | Van Hudson | Ben Lukins | 4
Epic03 | US-18 | Default Driven Display | As a standard ticket buyer, I want the system to have default values so that it is convinent for me. | Patrick Berzins | Van Hudson | 4
Epic03 | US-19 | Ticket Exchange | As a ticket buyer, I want the option to exchange my ticket for a different seat/show/performance so that I have the ability to adapt my plans. | Ben Lukins | Jayde Holbrook | 3
Epic03 | US-20 | Ticket Refund/Reimbursement | As a ticket buyer, I want to be to get my money back if the new ticket is of lesser value than the ticket exchanged so that I do not lose money in the exchange. | Van Hudson | Patrick Berzins | 5
Epic03 | US-21 | Ticket Exchange Difference | As a ticket buyer, I want to be able to exchange my ticket for a new ticket of more value and pay the difference so that I do not lose money already spent. | Van Hudson | Patrick Berzins | 5
Epic03 | US-22 | Responsive GUI | As a ticket buyer, I want to see that the system is responsive so that I am confident in the functionality of the system. | Patrick Berzins | Van Hudson | 3
Epic04 | US-23 | Tickets Sold At Door | As a ticket seller, I want to be able to record ticket sales at the door so that ALL sold tickets are marked as sold. | Patrick Berzins | Jayde Holbrook | 4
Epic04 | US-24 | Visual Indicator of Sold Seats (Admin) | As a ticket seller, I want to see which seats are already taken so that I do not sell seats that are unavailable. | Van Hudson | Jayde Holbrook | 4
Epic04 | US-25 | Ticket Information Export | As a ticket seller, I want to be able to export the address list and ticket assignment list from ticket sales so that I may have that information on file. | Nathaniel Smith | Jayde Holbrook | 3
Epic04 | US-26 | Ticket Information Import | As a ticket seller, I want to be able to import the address list and ticket assignment list so that if I have that data in separate files they can be added to the database. | Nathaniel Smith | Jayde Holbrook | 3
Epic04 | US-27 | Record Ticket Paid Status | As a ticket seller, I want to be able to view whether online sales are paid/unpaid so that I know if a patron still needs to pay for their ticket. | Patrick Berzins | Jayde Holbrook | 4
Epic04 | US-28 | Mark Reserved Tickets As Paid | As a ticket seller, I want to be able to mark tickets reserved online but paid at the door as paid so that all information is accurate. | Jayde Holbrook | Patrick Berzins | 4
Epic04 | US-29 | Store Season Ticket Holder Information | As a ticket seller, I want to have a list of all current season ticket holder's information so that it can be used to faciliate renewals for the next season. | Patrick Berzins | Ben Lukins | 4
Epic04 | US-30 | Update Season Ticket Holder Information | As a ticket seller, I want to update season ticket holder information so that all information is accurate. | Jayde Holbrook | Patrick Berzins | 4
Epic04 | US-31 | Change Standard Ticket Price | As a ticket seller, I want to be able to change the price of a ticket so that I can make a profit on the performances. | Patrick Berzins | Ben Lukins | 4
Epic04 | US-32 | Edit show data | As a ticket seller, I want to edit data by show so that I do not interfere with other productions. | Patrick Berzins | Ben Lukins | 5
Epic04 | US-33 | Access admin privileges | As a ticket seller, I want to enter my password to the admin page so that I may access admin priviledges. | Patrick Berzins | Ben Lukins | 3

## Tasks
Tracking Number | Open Date | Status | Closed Date | User Story | Assigned to | Title | Task Details | Closure Details
TSK-01 | 2023-01-19 | Closed-Resolved | 2023-01-24 | US-01 | ALL | Development Research | Research into what platforms and architectures will be used | Team decided to use Firebase and ReactJS
TSK-02 | 2023-01-23 | Closed-Resolved | 2023-01-26 | US-02 | ALL | Work on presentation | Help fill out the slides for the presentation | Presented completed slide show
TSK-03 | 2023-01-23 | Closed-Resolved | 2023-01-26 | US-02 | ALL | Work on SDP doc | FIll out assigned sections of the SDP document | SDP was completed on time
TSK-04 | 2023-01-31 | Closed-Resolved | 2023-02-02 | US-03 | ALL | Work on User Stories | Create initial list of user stories for the project | See User Stories page for completed US
TSK-05 | 2023-02-02 | Closed-Resolved | 2023-02-07 | US-03 | ALL | Work on Requirements | Translate user stories into requirements for the system | First round of requirements were created together
TSK-06 | 2023-02-07 | Closed-Resolved | 2023-02-14 | US-04 | ALL | Design Prototype | Design and come up with ideas for GUI prototype | Designed Prototype in Figma click link
TSK-07 | 2023-02-07 | Closed-Resolved | 2023-02-14 | US-03 | ALL | Work on User Story Presentation | Create presentation for sprint 2 | Completed slide show
TSK-08 | 2023-02-09 | Closed-Resolved | 2023-02-23 | US-02 | Nathaniel Smith | Create UML Diagram | Create a UML/Class Diagram for the application | Completed sufficiently for initial coding work to begin
TSK-09 | 2023-02-14 | Closed-Resolved | 2023-02-14 | US-01 | Jayde Holbrook | Set up Node.JS on the GitHub | Create a basic Node.JS project and push it to the GitHub | Successfully pushed project to the GitHub
TSK-10 | 2023-02-23 | Closed-Resolved | 2023-02-28 | US-04 | Van Hudson | Create a React.JS demo | Create a simple React.js project and push it to the GitHub | Pushed project to GitHub and worked with team to ensure it worked across team member computers
TSK-11 | 2023-02-23 | Closed-Resolved | 2023-02-28 | US-03 | Jayde Holbrook | Create sample JSON into Node.JS | Create a sample JSON file to set-up pulling into Node.JS | Discussed with team at team meeting and pushed to GitHub
TSK-12 | 2023-02-28 | Closed-Resolved | 2023-03-07 | US-02 | ALL | Work on Presentation 3 | Create presentation for sprint 3/architecture | Finished and presented Sprint 3 work
TSK-13 | 2023-03-02 | Closed-Resolved | 2023-03-09 | US-04 | Patrick Berzins | Create a React.JS demo using TypeScript | Set up TypeScript in React and make a small demo | Made a simple page navigation demo using react typecript
TSK-14 | 2023-03-02 | Closed-Resolved | 2023-03-09 | US-02 | Van Hudson | Update SDP | Update the SDP in preparation for Presentation 3 | New version of SDP placed in folder
TSK-15 | 2023-03-04 | Closed-Resolved | 2023-03-28 | US-25/26 | Nathaniel Smith | Create JSON Handler | Implement a class to handle the importing and exporting of ticket information between a file of the user's choice and the program. | First pass of JSONHandler was created; Not marked as resolved until it was reviewed and merged into master branch
TSK-16 | 2023-03-04 | Closed-Resolved | 2023-03-09 | US-13 | Jayde Holbrook | Create SeatSection class | Create SeatSection class based off of UML diagram to be used in the system | First pass of SeatSection was created; Not marked as resolved until it was reviewed and merged into master branch
TSK-17 | 2023-03-04 | Closed-Resolved | 2023-03-09 | US-11 | Jayde Holbrook | Create Venue class | Create Venue class based off of UML diagram to be used in the system | First pass of Venue was created; Not marked as resolved until it was reviewed and merged into master branch
TSK-18 | 2023-03-04 | Closed-Resolved | 2023-03-09 | US-13 | Jayde Holbrook | Create Seat class | Create Seat class based off of UML diagram to be used in the system | First pass of Seat was created; Not marked as resolved until it was reviewed and merged into master branch
TSK-19 | 2023-03-04 | Closed-Resolved | 2023-03-21 | US-10 | Ben Lukins | Create Show class | Create Show class based off of UML diagram to be used in the system | First pass of Show was created; Not marked as resolved until it was reviewed and merged into master branch
TSK-20 | 2023-03-04 | Closed-Resolved | 2023-03-21 | US-12 | Ben Lukins | Create Performance class | Create Performance class based off of UML diagram to be used in the system | First pass of Performance was created; Not marked as resolved until it was reviewed and merged into master branch
TSK-21 | 2023-03-04 | Closed-Resolved | 2023-03-21 | US-19 | Ben Lukins | Create Ticket class | Create Ticket class based off of UML diagram to be used in the system | First pass of Ticket was created; Not marked as resolved until it was reviewed and merged into master branch
TSK-22 | 2023-03-09 | Closed-Resolved | 2023-04-06 | US-04 | Van Hudson | Implement front-end design for season ticket tab | Create the front-end design for the season ticket tab of React | Season Ticket checkout page implemented as planned.
TSK-23 | 2023-03-09 | Closed-Resolved | 2023-03-28 | US-04 | Van Hudson | Implement page flow for ticket buyers | Design and implement the page flow for ticket buyers in React | Page flow for ticket buyers has been implemented; tracking data between pages works
TSK-24 | 2023-03-09 | Closed-Resolved | 2023-03-20 | US-22 | Patrick Berzins | admin pages | create ui and page flow for admin interactions | Admin pages created
TSK-25 | 2023-03-09 | Closed-Resolved | 2023-03-23 | US-14 | Jayde Holbrook | Create Attendee class | Create Attendee class based off of UML diagram to be used in the system | First pass of Attendee was created
TSK-26 | 2023-03-09 | Closed-Resolved | 2023-03-23 | US-23 | Jayde Holbrook | Create Purchase class | Create Purchase class based off of UML diagram to be used in the system | First pass of Purchase was created; Multiple handlers (PurchaseHandler, TicketSalesAtDoorHandler, OnlineTicketSalesHandler) were combined into Purchase to avoid redundancy
TSK-27 | 2023-03-09 | Closed-Resolved | 2023-03-23 | US-30 | Jayde Holbrook | Create SeasonTicketHolder class | Create SeasonTicketHolder class based off of UML diagram to be used in the system | First pass of SeasonTicketHolder was created
TSK-28 | 2023-03-23 | Closed-Resolved | 2023-03-28 | US-19 | Jayde Holbrook | Create ExchangeHandler class | Create ExchangeHandler based off of UML diagram to be used in the system | First pass of ExchangeHandler was created
TSK-29 | 2023-03-19 | Closed-Resolved | 2023-03-31 | US-33 | Ben Lukins | Backend/Frontend communication test | Create a way for the backend to handle requests from the frontend and respond with necessary data | Communication established
TSK-30 | 2023-03-19 | Closed-Withdrawn | 2023-04-15 | US-05 | Ben Lukins | Unit testing demo | Create a unit testing example with Jest | Switching to integration testing
TSK-31 | 2023-03-28 | Closed-Resolved | 2023-04-06 | US-10 | Van Hudson | User View Available Performances | Create the frontend UI for viewing performances | First and second pass of user flow completed.
TSK-32 | 2023-03-28 | Closed-Withdrawn | 2023-04-11 | US-07 | Van Hudson | Implement user filtering by venue | Create the frontent UI for displaying filtered results (venue) | Decided to scrap search functionality; not a functional requirement
TSK-33 | 2023-03-28 | Closed-Withdrawn | 2023-04-11 | US-09 | Van Hudson | Implement user filtering by category | Create the frontent UI for displaying filtered results (category) | Decided to scrap search functionality; not a functional requirement
TSK-34 | 2023-03-28 | Closed-Withdrawn | 2023-04-11 | US-08 | Van Hudson | Implement user filtering by date | Create the frontent UI for displaying filtered results (date) | Decided to scrap search functionality; not a functional requirement
TSK-35 | 2023-03-30 | Closed-Resolved | 2023-03-30 | US-26 | ALL | Integrate JSON serializer library | Integrate JSON serializer library to use in system | The library has been integrated and functions correctly by Ben, Van, and Jayde
TSK-36 | 2023-03-30 | Closed-Resolved | 2023-04-03 | US-25 | Jayde Holbrook | Create Seat deserializer | Create Seat derserializer using the JSON library | Seat data can now be deserialized
TSK-37 | 2023-03-30 | Closed-Resolved | 2023-04-03 | US-25 | Jayde Holbrook | Create SeatSection deserializer | Create SeatSection derserializer using the JSON library | SeatSection data can now be deserialized
TSK-38 | 2023-03-30 | Closed-Resolved | 2023-04-04 | US-25 | Jayde Holbrook | Create Performance deserializer | Create Performance derserializer using the JSON library | Performance data can now be deserialized; slight delay because of circular structure issue that was resolved
TSK-39 | 2023-03-30 | Closed-Resolved | 2023-04-04 | US-25 | Jayde Holbrook | Create Ticket deserializer | Create Ticket derserializer using the JSON library | Ticket data can now be deserialized; slight delay because of circular structure issue that was resovled
TSK-40 | 2023-03-30 | Closed-Resolved | 2023-04-03 | US-25 | Jayde Holbrook | Create Attendee deserializer | Create Attendee derserializer using the JSON library | Attendee data can now be deserialized
TSK-41 | 2023-03-30 | Closed-Resolved | 2023-04-03 | US-25 | Jayde Holbrook | Create SeasonTicketHolder deserializer | Create SeasonTicketHolder derserializer using the JSON library | SeasonTicketHolder data can now be deserialized
TSK-42 | 2023-03-30 | Closed-Resolved | 2023-04-04 | US-25 | Jayde Holbrook | Create Show deserializer | Create Show derserializer using the JSON library | Show data can now be deserialized; slight delay because of circular structure issue that was resovled
TSK-43 | 2023-03-30 | Closed-Resolved | 2023-04-03 | US-25 | Jayde Holbrook | Create Venue deserializer | Create Venue derserializer using the JSON library | Venue data can now be deserialized
TSK-44 | 2023-03-30 | Closed-Resolved | 2023-04-04 | US-25 | Jayde Holbrook | Create Purchase deserializer | Create Purchase deserializer using the JSON library | Purchase data can now be deserialized; slight delay because of circular structure issue that was resovled
TSK-45 | 2023-03-30 | Closed-Resolved | 2023-04-15 | US-22 | Nathaniel Smith | Create System Class | Create the System class in TypeScript based off of UML diagram | Base System class created and built upon
TSK-46 | 2023-04-06 | Closed-Resolved | 2023-04-15 | US-23 | Van Hudson | Implement user selecting performance | Integrate existing frontend design with backend classes in order to visually represent real data. | Users can select performances they would like to buy tickets to
TSK-47 | 2023-04-06 | Closed-Resolved | 2023-04-15 | US-24 | Van Hudson | Implement user selecting seat | Implement the funcitonality for users to select a seat. | Implemented successfully
TSK-48 | 2023-04-08 | Closed-Resolved | 2023-04-08 | US-29 | Patrick Berzins | GET json from backend | frontend for getting seat data from backend | Communication and information passing works
TSK-49 | 2023-03-21 | Closed-Resolved | 2023-03-30 | US-33 | Patrick Berzins | Admin access privilages | admin can log into a password protected side of website. | You can only access the admin page through the password
TSK-50 | 2023-04-04 | Closed-Resolved | 2023-04-08 | US-25 | Jayde Holbrook | Basic comments for classes | All classes need basic function comments | All current classes now have basic function comments
TSK-51 | 2023-04-04 | Closed-Resolved | 2023-04-08 | US-01 | Jayde Holbrook | Verifying deserialization information | Going back through alll deserialization functions to verify that no information is lost in conversion | No information is being lost in conversion
TSK-52 | 2023-03-30 | Closed-Resolved | 2023-04-07 | US-19 | Ben Lukins | Generate Confirmation Numbers | Create a method to generate globally unique ID's for purchases | Unique confirmation numbers now generate for each purchase
TSK-53 | 2023-04-12 | Closed-Resolved | 2023-04-12 | US-23 | Jayde Holbrook | Add a DateTime object to Purchase | Update Purchase class to fit new needs | Purchase was updated to fit new needs
TSK-54 | 2023-04-11 | Closed-Resolved | 2023-04-27 | US-06 | Jayde Holbrook | Write User Guide draft | Create a User Guide that addresses both ticket sellers and ticket buyers | User Guide was written
TSK-55 | 2023-04-13 | Closed-Resolved | 2023-04-15 | US-25/26 | Jayde Holbrook | Create CSV Handler | Need a CSV Handler to allow the ticket seller to export in json or csv | Now allows for the use of exporting or importing CSV files
TSK-56 | 2023-04-13 | Closed-Resolved | 2023-04-14 | US-25/26 | Jayde Holbrook | Update JSONHandler | Update JSONHandler to allow for exporting and importing SeasonTicketHolder information | Update to add these functions for use in front-end admin GUI
TSK-35 | 2023-04-13 | Closed-Resolved | 2023-04-18 | US-29 | Patrick Berzins | implement season ticket holder information | ability to view and edit season ticket holder info | Implemented successfully
TSK-36 | 2023-04-13 | Closed-Resolved | 2023-04-18 | US-31 | Patrick Berzins | implement edit ticket price default | ability to set default prices for theatre sections | Implemented successfully
TSK-37 | 2023-04-06 | Closed-Resolved | 2023-04-15 | US-32 | Patrick Berzins | Edit Show Data | allow admin to edit data for shows | admin can add, and delete shows from the list
TASK-60 | 2023-04-03 | Closed-Resolved | 2023-04-16 | US-18 | Van Hudson | Set GUI/system with default driven options | Facilitate default options in GUI | default payment option is "pay online"
TSK-34 | 2023-04-11 | Closed-Resolved | 2023-04-15 | US-29 | Patrick Berzins | store season ticket holder info | create a gui that shows season ticket holder info | Implemented successfully
TSK-62 | 2023-04-03 | Closed-Resolved | 2023-04-11 | US-15 | Van Hudson | Implement user selecting a payment method | Create GUI option for selecting pay online or pay in person | implemented successfully
TSK-63 | 2023-04-06 | Closed-Resolved | 2023-04-23 | US-13 | Van Hudson | Implement user purchasing a selected seat | Create GUI for purchasing a selected seat and ensure it works with backend | implemented successfully
TSK-64 | 2023-04-16 | Closed-Resolved | 2023-04-23 | US-14 | Van Hudson | Implement user entering payment information | Create GUI for entering payment information | implemented successfully
TSK-65 | 2023-04-10 | Closed-Resolved | 2023-04-16 | US-11 | Van Hudson | Build GUI that shows available seats | Make sure that visual indicator works to show which seats are actually available | Taken seats are greyed-out
TSK-66 | 2023-04-23 | Closed-Resolved | 2023-04-28 | US-06 | ALL | Final prep and Delivery | Prepare for final delivery by prepping application and documentation | Final delivery of project was made
TSK-67 | 2023-04-23 | Closed-Resolved | 2023-04-28 | US-05 | Ben Lukins | Write Test Cases | Fill out Weekly Report with all test cases | All test cases written and tested

## Schedule
Title | Scheduled Start Date | Actual Start Date | Scheduled Complete Date | Actual Complete Date | Assigned to | Verified by
Team Report Week 1 | 2023-01-17 | 2023-01-17 | 2023-01-22 | 2023-01-22 | ALL | Jayde Holbrook
Team Report Week 2 | 2023-01-24 | 2023-01-24 | 2023-01-29 | 2023-01-29 | ALL | Jayde Holbrook
Team Report Week 3 | 2023-01-31 | 2023-01-31 | 2023-02-05 | 2023-02-05 | ALL | Jayde Holbrook
Team Report Week 4 | 2023-02-07 | 2023-02-07 | 2023-02-12 | 2023-02-12 | ALL | Jayde Holbrook
Team Report Week 5 | 2023-02-14 | 2023-02-14 | 2023-02-19 | 2023-02-19 | ALL | Jayde Holbrook
Team Report Week 6 | 2023-02-21 | 2023-02-21 | 2023-02-26 | 2023-02-26 | ALL | Jayde Holbrook
Team Report Week 7 | 2023-02-28 | 2023-02-28 | 2023-03-05 | 2023-03-05 | ALL | Jayde Holbrook
Team Report Week 8 | 2023-03-07 | 2023-03-07 | 2023-03-12 | 2023-03-12 | ALL | Jayde Holbrook
Team Report Week 9 | 2023-03-14 | 2023-03-14 | 2023-03-19 | 2023-03-26 | ALL | Jayde Holbrook | * There is a shift in scheduled vs actual due to Spring Break
Team Report Week 10 | 2023-03-21 | 2023-03-26 | 2023-03-26 | 2023-04-02 | ALL | Jayde Holbrook
Team Report Week 11 | 2023-03-28 | 2023-04-03 | 2023-04-02 | 2023-04-09 | ALL | Jayde Holbrook
Team Report Week 12 | 2023-04-04 | 2023-04-11 | 2023-04-09 | 2023-04-16 | ALL | Jayde Holbrook
Team Report Week 13 | 2023-04-11 | 2023-04-17 | 2023-04-16 | 2023-04-23 | ALL | Jayde Holbrook
Team Report Week 14 | 2023-04-18 | 2023-04-24 | 2023-04-23 | 2023-04-28 | ALL | Jayde Holbrook
SDP Submission | 2023-01-17 | 2023-01-23 | 2023-01-26 | 2023-01-26 | ALL | Jayde Holbrook
User Stories /Requirements | 2023-01-31 | 2023-01-31 | 2023-02-16 | 2023-02-21 | ALL | ALL
Architectural Design | 2023-02-21 | 2023-02-23 | 2023-03-07 | 2023-03-07 | ALL | ALL
Preliminary GUI Design | 2023-03-21 | 2023-03-09 | 2023-03-30 | 2023-04-06 | ALL | ALL
Beta Tesing and Demo | 2023-04-03 | 2023-04-07 | 2023-04-20 | 2023-04-18 | ALL | ALL
Final delivery | 2023-04-20 | 2023-04-18 | 2023-04-18 | 2023-04-28 | ALL | Jayde Holbrook
Formulas:
Scheduled Start Date = [Scheduled Start Date, row above]+7
Scheduled Complete Date = [Scheduled Complete Date, row above]+7

## Requirements
Parent Unit | Requirement ID | Title | Requirement Statement (English) | Additonal Information | Assigned to
US-06 | Rqmt01 | User Tutorial | TickIt shall provide a tutorial on the ticket buying process that is easily located by the ticket buyer. | This can be found in the User Guide | Jayde Holbrook
US-10 | Rqmt02 | View Performances | TickIt shall display all upcoming performances in a graphical user interface. |  | Patrick Berzins
US-11 | Rqmt03 | View Seats | TickIt shall display all seats for a ticket buyer's selected performance. |  | Van Hudson
US-12 | Rqmt04 | Select Performance | TickIt shall allow ticket buyers to select a specific performance to view additional details of. | This would take the ticket buyer to the GUI of seats for that performance. | Patrick Berzins
US-13 | Rqmt05 | User Seat Selection | TickIt shall allow a user to select an available seat |  | Van Hudson
US-14 | Rqmt06 | User Input Payment Information | TickIt shall allow a user to enter payment information |  | Van Hudson
US-15 | Rqmt07 | User Payment Method | TickIt shall provide a user with multiple payment method options |  | Van Hudson
US-16 | Rqmt08 | Visual Seat Indiciation | TickIt shall provide visual indications of section, row, seat number, and wheelchair accessibility. |  | Van Hudson | Backend Support: Ben Lukins
US-17 | Rqmt09 | Visual Indicator of Sold Seats (Public) | TickIt shall provide a visual indication that a seat is or is not available |  | Van Hudson
US-18 | Rqmt10 | Default Driven Display | TickIt shall provide default selections based on an average user's choices |  | Van Hudson
US-04 | Rqmt11 | clear GUI | TickIt shall have a UI that is easy to navigate and understand as for first time users |  | Patrick Berzins
US-19 | Rqmt12 | Ticket Exchange | TickIt shall allow users to exchange tickets for another ticket |  | Jayde Holbrook
US-21 | Rqmt13 | Ticket Exchange difference | If the user exchanges their current ticket for a more expensive one, TickIt shall only charge for the difference bwteen the two. |  | Jayde Holbrook
US-22 | Rqmt14 | Responsive GUI | TickIt shall provide feedback or confirmations to the user so that the user knows that the system is working and their interacitons are being recieved. |  | Patrick Berzins
US-23 | Rqmt15 | Tickets Sold At Door | TickIt shall allow ticket sellers to record tickets sold at the door. |  | Ben Lukins
US-24 | Rqmt16 | Visual Indicator of Sold Seats (Admin) | TickIt shall display sold seats to ticket sellers. |  | Patrick Berzins
US-25 | Rqmt17 | Ticket Information Export | TickIt shall allow ticket sellers to export the current address list and ticket assignment list to a database in the file format of their choice. | Available file formats include JSON, CSV | Nathaniel Smith
US-26 | Rqmt18 | Ticket Information Import | TickIt shall allow ticket sellers to import an address list and ticket assignment list from a database in the file format of their choice. |  | Nathaniel Smith
US-27 | Rqmt19 | Record Ticket Paid Status | TickIt shall allow ticket sellers to view the payment status of reserved pay-at-the-door tickets. |  | Ben Lukins
US-28 | Rqmt20 | Mark Reserved Tickets As Paid | TickIt shall allow ticket sellers to mark reserved pay-at-the-door tickets as paid. |  | Patrick Berzins | Backend support: Ben Lukins
US-29 | Rqmt21 | Store Season Ticket Holder Information | Tickit shall allow ticket sellers to see a list of all current season ticket holders and their information. | This will be used to facilitate renewals for the next season. | Patrick Berzins
US-30 | Rqmt22 | Update Season Ticket Holder Information | TickIt shall allow ticket sellers to change the information of season ticket holders. |  | Ben Lukins
US-31 | Rqmt23 | Change Standard Ticket Price | TickIt shall allow ticket sellers to change the price of a ticket. |  | Ben Lukins
US-32 | Rqmt24 | Edit show data | TickIt shall allow ticket sellers to edit the data of only their own organization's production(s). |  | Patrick Berzins | Backend support: Ben Lukins
US-33 | Rqmt25 | Access admin privileges | TickIt shall allow ticket sellers to access "administrator" pages using a password. | Each organization has one representative who keeps their own password. | Patrick Berzins | Backend support: Ben Lukins

## Risk Tracking
Risk ID | Risk Title | Likelihood | Impact Level | Risk Score | Mitigation Steps
Risk-01 | Team Member Drops Out/Gets Fired | 1 | 4 | 4 | Verify that everyone would like to graduate
Risk-02 | COVID | 3 | 3 | 9 | Wash your hands and stay home if sick
Risk-03 | Class/work conflicts | 1 | 3 | 3 | Communicate when we are and aren't available
Risk-04 | Member(s) not knowing required tools | 4 | 2 | 8 | Using online resources to learn
Risk-05 | Technology breaks down | 2 | 4 | 8 | Using well-known and reliable resources and redundancy of personal technology
Risk-06 | Platforms do not work together | 1.5 | 5 | 7.5 | Proper research beforehand
Risk-07 | Platforms require payment to use | 2 | 4 | 8 | Proper research beforehand. Otherwise, research alternate platforms

## Test Cases
Test Case ID | Requirement(s) / User Story | Title | Description | Assigned to: | Status
TC-01 | Rqmt 23 | Policies and Prices | To test whether policies and prices are configurable for Playhouse: Launch app > Click "Admin Login" > Enter valid password > Click "Default Prices" > Click "Edit" on each section in Playhouse> Change each section price to a different value > Check that it updates list > Click "Back" > Click "Manage Listings" > Click "Create Show" > Enter event name > Select Playhouse > Verify each section has price entered previously in "Default Prices" page | Ben Lukins | Tested-Passed
TC-02 | Rqmt 23 | Policies and Prices | To test whether policies and prices are configurable for Concert Hall: Launch app > Click "Admin Login" > Enter valid password > Click "Default Prices" > Click "Edit" on each section in Concert Hall> Change each section price to a different value > Check that it updates list > Click "Back" > Click "Manage Listings" > Click "Create Show" > Enter event name > Select Concert Hall> Verify each section has price entered previously in "Default Prices" page | Ben Lukins | Tested-Passed
TC-03 | Rqmt 23 | Policies and Prices input validation | To test whether the application checks for negative defaults: Launch app > Click "Admin Login" > Enter valid password > Click "Default Prices" > Click "Edit" on each section in Playhouse > Change each section price to a different NEGATIVE value > Verify that it doesn't let you submit | Ben Lukins | Tested-Passed
TC-04 | Rqmt 06 + 07 + 15 | Payment Choice | Check that the app lets you pay by cash, check, or credit card: Launch app > Click on "Purchase tickets" for any performance > Select any seat > Click "Check Out" > Verify that there is a way to pay with cash, check or credit card | Ben Lukins | Tested-Passed
TC-05 | Rqmt 23 | Prices Vary By Section | Check that different sections have different prices: Launch app > Click on "Purchase Tickets" for any performance > Select any seat in any section > Click "Check Out" > Make note of "Total Price" value > Return to home page > Click "Purchase Tickets" on the same performance > Select any seat in a different section than the previous check > Click "Check Out" > Verify that the "Total Price" value is different than the previous ticket's price | Ben Lukins | Tested-Passed
TC-06 | Rqmt 21 | Season Ticket Holder Recording | Check that season ticket holders' info is recorded | Ben Lukins | Tested-Passed
TC-07 | Rqmt 12 + 13 | Ticket identification | Check tickets identified by section, row, seat number, and disabled accessibility: Launch app > Click "Purchase Tickets" on any performance > Select any seat > Verify that the app identifies the section, row, and seat number of the seat you selected | Ben Lukins | Tested-Passed
TC-08 | Rqmt 03 + 05 + 08 + 09 | Seat Selection - Concert Hall | Check that users can select seats in a visual display with available seats: Launch app > Click "Purchase Tickets" on any performance in the Concet Hall > Verify that the page shows the map of the Concert Hall > Attempt to click on an available seat > Verify that you are allowed to select it > Attempt to click on unavailable seat > Verify that you cannot select that seat | Ben Lukins | Tested-Passed
TC-09 | Rqmt 03 + 05 + 08 + 09 | Seat Selection - Playhouse | Check that users can select seats in a visual display with available seats: Launch app > Click "Purchase Tickets" on any performance in the Playhouse > Verify that the page shows the map of the Playhouse > Attempt to click on an available seat > Verify that you are allowed to select it > Attempt to click on unavailable seat > Verify that you cannot select that seat | Ben Lukins | Tested-Passed
TC-10 | Rqmt 24 | Visual event list | Check that events are displayed visually: Launch app > Verify that there is a visual list of events with each event's name, venue, date, and time | Ben Lukins | Tested-Passed
TC-11 | Rqmt 19 + 20 | Visual purchase list | Check that the purchase data is displayed visually: Launch app > Click "Admin Login" > Click "Ticket Stuff" > Verify that the list of purchases displays all information visually | Ben Lukins | Tested-Passed
TC-12 | Rqmt 21 + 22 | Visual Season Pass list | Check that the list of season ticket holders is displayed visually: Launch app > Click "Admin Login" > Click "Season Passes" > Verify that the list of purchases displays all information visually | Ben Lukins | Tested-Passed
TC-13 | Rqmt 23 | Visual default price list | Check that the app displays all default prices visually: Launch app > Click "Admin Login" > Click "Default Prices" > Verify that the list of all default prices is displayed visually | Ben Lukins | Tested-Passed
TC-14 | Rqmt 10 | Default driven checkout | Check that the checkout page uses default-driven displays: Launch app > Click "Purchase Tickets" on any purchase > Select any seat > Click "Check Out" > Verify that the checkout page defaults to "None" for discounts > Verify that the page defaults to "Pay Online" | Ben Lukins | Tested-Passed
TC-15 | Rqmt 10 | Default driven prices | Check that creating performances for admins is default-driven: Launch app > Click "Admin Login" > Click "Manage Listings" > Click "Create Show" > Select any Venue > Verify that the default prices are automatically filled in for each section | Ben Lukins | Tested-Passed
TC-16 | Rqmt 11 + 14 | Visible mechanisms | Verify that all actions can be taken with button presses and field fills within the application, no external input or command line work is necessary | Ben Lukins | Tested-Passed
TC-17 | Rqmt 14 | Timely Feedback | Verify that each action updates the webpage in a timely fashion, no action takes longer than 1 second | Ben Lukins | Tested-Passed
TC-18 | Rqmt 21 | Season Ticket List | Launch app > Click "Admin Login" > Enter valid password > Click "Season Passes" > Make note of list contents and add a season pass if empty > Exit App > Relaunch app > Follow same procedure to access Season Pass list > Verify that the information is still retained by the system, beyond shut-down | Ben Lukins | Tested-Passed
TC-19 | Rqmt 22 | Season Ticket Edits | Check that season ticket holders' info can be edited: Launch app > Click "Admin Login" > Enter valid password > Click "Season Passes" > Click "Edit" on any season ticket holder in the table > Edit all pieces of information > Click "Submit" > Verify that the previously entered information is now present in the table | Ben Lukins | Tested-Passed
TC-20 | Rqmt 09 + 16 | Seats marked when sold | Launch app > Click "Purchase Tickets" on any performance > Select any ticket > Click "Check Out" > Fill out all necessary information > Click "Place Order" > Click "Return to Home" > Click "Purchase Tickets" on the same performance > Verify that the seat previously selected and purchased is visually distinct from available seats and no longer selectable | Ben Lukins | Tested-Passed
TC-21 | Rqmt 20 | Change Ticket Status | Launch app > Click "Admin Login" > Click "Ticket Stuff" > Click "Edit" on any purchase > Select new ticket status > Click "Submit" > Verify that the status changes | Ben Lukins | Tested-Passed
TC-22 | Rqmt 15 | Admin-recorded reservation | Check that admins can reserve seats at the door: Launch app > Click "Admin Login" > Enter valid password > Click "Ticket Stuff" > Click "Add Purchase" > Select a show > Select any seat > Click "Check Out" > Fill in required info > Click "Place Order" > Verify that the new purchase was added to the list | Ben Lukins | Tested-Passed
TC-23 | Rqmt 12 + 13 | Ticket Exchange | Check that people can exchange tickets with a confirmation number: | Ben Lukins | Tested-Passed
TC-24 | Rqmt 17 | Season Ticket list export | Check that season ticket holder list can be exported: Launch app > Click "Admin Login" > Enter valid password > Click "Season Passes" > Click "Export Data" > Choose a file format > Click "Export" > Verify that a season ticket file was created in the main tick-it directory | Ben Lukins | Tested-Passed
TC-25 | Rqmt 18 | Season ticket list import | Check that season ticket holder list can be imported: Launch app > Click "Admin Login" > Enter valid password > Click "Season Passes" > Click "Import Data" > Click "Browse" > Select a JSON file > Click "Submit" > Verify that the information in the page was updated with your imported info | Ben Lukins | Tested-Passed
TC-26 | Rqmt 06 + 15 | Ticket Purchase phone num input validation | Launch app > Click "Purchase tickets" on any performance > Select any seat > Click "Check Out" > Enter letters in the phone number field > Click "Place Order" > Verify that it doesn't let you place your order | Ben Lukins | Tested-Passed
TC-27 | Rqmt 06 + 07 + 15 | Ticket purchase credit card input validation | Launch app > Click "Purchase tickets" on any performance > Select any seat > Click "Check Out" > Enter letters in the credit card number, expiration date, security code, and zip code fields > Click "Place Order" > Verify that it doesn't let you place your order | Ben Lukins | Tested-Passed
TC-28 | Rqmt 25 | Password protected admin | Check that admin pages are protected by password: Launch app > Click "Admin Login" > Enter incorrect password > Verify that it does not redirect you to admin page | Ben Lukins | Tested-Passed

## Problem Reports
Number | Title | Test Case (if any) | Date Open | Status | Assigned to: | Verified by: | Date Closed
SPR-01 | Circular structure deserialization issues | NA | 2023-04-01 | Corrected | ALL | Jayde Holbrook | 2023-04-04
SPR-02 | Demo Bug | NA | 2023-04-18 | Corrected | Ben Lukins | Jayde Holbrook | 2023-04-18
SPR-03 | No input check for default prices, no min price | TC-03 | 2023-04-23 | Corrected | Patrick Berzins | Ben Lukins | 2023-04-27
SPR-04 | No input type check for updating season pass phone num |  | 2023-04-23 | Corrected | Patrick Berzins | Ben Lukins | 2023-04-27
SPR-05 | Can't change ticket status in admin page. Also sometimes breaks everything, backend hangs, when you threaten its life it works | TC-22 | 2023-04-23 | Corrected | Ben Lukins | Van Hudson | 2023-04-23
SPR-06 | Can create a purchase from admin page when there are no shows that exist |  | 2023-04-24 | Corrected | Patrick Berzins | Ben Lukins | 2023-04-27
SPR-07 | Update ticket status page doesn't auto-refresh |  | 2023-04-28 | Corrected | Ben Lukins | Jayde Holbrook | 2023-04-28
SPR-08
SPR-09
SPR-10
SPR-11
SPR-12
SPR-13
SPR-14
SPR-15
SPR-16
SPR-17
SPR-18
SPR-19
SPR-20
SPR-21
SPR-22
SPR-23
SPR-24
SPR-25
SPR-26
SPR-27
SPR-28
SPR-29
SPR-30

## Lists
Primary Role | Meeting Role | Action Item Status | Term Start Date | Term End Date | Test Status | SPR Status | Assignments To
Team Lead | Moderator | Open | 2023-01-09 | 2023-04-28 | Not Tested | Open | Patrick Berzins
Technical Lead | Recorder | Closed-Resolved |  |  | In-Process | In-Work | Jayde Holbrook
Technical Writer | Present | Closed-Withdrawn |  |  | Tested-Failed | Corrected | Van Hudson
Test Lead | Absent - Known | Pending |  |  | Tested-Passed | Closed | Ben Lukins
Tools Lead | Absent - Unknown | [5 empty] | Nathaniel Smith
CM Lead | [6 empty] | ALL
Quality Lead | [6 empty] | TBD
GUI Lead | [6 empty] | N/A
Front End Development
These are agreed-upon terms to be used throughout the semester. If new ones are needed, or old ones abandoned, modify these appropriately